MINISTRY OF WATER, SANITATION AND IRRIGATION

STATE DEPARTMENT FOR IRRIGATION

PROGRAMME PERFORMANCE REVIEW

FOR

FINANCIAL YEAR 2023/24 – 2025/26

Table of Contents

1.0	INTRODUCTION	4

2.1 REVIEW OF SUB-SECTOR PROGRAMME PERFORMANCE FY 2023/24 – 2025/26	4

2.2 ANALYSIS OF EXPENDITURE TRENDS FOR THE FY 2023/24 – FY 2025/26	14

Table 2. 3: Analysis of Development Approved Budget Vs Actual Expenditure (Ksh. Million)	15

Table 2. 4: Analysis of Programme Approved Budget Vs Actual Expenditure (Ksh. Million)	15

Table 2. 5: Analysis of Programme Approved Budget Vs Actual Expenditure (Ksh. Million)	16

Table 2. 6: Analysis of SAGAs Recurrent Budget Vs. Actual Expenditure (Ksh. Million)	18

2.3 ANALYSIS OF PERFORMANCE OF CAPITAL PROJECTS FY 2023/4 – 2025/26	20

Table 2. 7: Analysis of Performance of Capital Projects FY 2023/24 – 2025/26	20

2.4 REVIEW OF PENDING BILLS	45

Table 2. 8: Summary of Pending Bills	45

2.5 SUMMARY OF COURT AWARDS	46

Table 2. 9: Summary of Court Awards	46

List of Tables

Table 2. 1: Sub Sector Programme Performance Review	5

Table 2. 2: Analysis of Recurrent Expenditure (KSh. Million)	14

Table 2. 3: Analysis of Development Approved Budget Vs Actual Expenditure (Ksh. Million)	15

Table 2. 4: Analysis of Programme Approved Budget Vs Actual Expenditure (Ksh. Million)	15

Table 2. 5: Analysis of Programme Approved Budget Vs Actual Expenditure (Ksh. Million)	16

Table 2. 6: Analysis of SAGAs Recurrent Budget Vs. Actual Expenditure (Ksh. Million)	18

Table 2. 7: Analysis of Performance of Capital Projects FY 2023/24 – 2025/26	20

Table 2. 8: Summary of Pending Bills	47

Table 2. 9: Summary of Court Awards	48

# INTRODUCTION

During the period FY 2023/24 – 2025/26, the Irrigation sub-sector implemented programmes in line with State Department’s Strategic Plan 2023 – 2027. These programmes included: Irrigation and Land Reclamation; Water Harvesting and Storage for Irrigation; and Water Storage and Flood Control; and General Administration, Planning and Support Services. The programmes were designed to support: completion of ongoing interventions under the Bottom-Up Economic Transformation Agenda; and priorities of the Third and the Fourth Medium Term Plans of the Kenya Vision 2030. The programmes are geared towards fulfilling the requirements for furtherance and implementation of the Constitution and in line with the mandate of the irrigation sub-sector to drive agricultural transformation, address poverty and food insecurity and build resilience against climate variability by advancing irrigation expansion, land reclamation, water harvesting and flood control measures.

This report therefore presents a review of the sub-sector’s programmes performance for FY 2023/24 – 2025/26 and analysis of expenditure trends and performance of capital projects for the period under review. It also presents a review of pending bills that were incurred during FY 2023/24 – 2025/26 and finally presents a summary of court awards.

# 2.1 REVIEW OF SUB-SECTOR PROGRAMME PERFORMANCE FY 2023/24 – 2025/26

This section presents a review of the sub-sector’s programmes performance by detailing the Delivery Units, Key Outputs, Key Performance Indicators, Planned Targets and Achieved Targets for the FY 2022/23-2024/25. This information is presented in Table 2. 1.

Table 2. 1: Sub Sector Programme Performance Review

| Programme | Delivery Unit | Key Outputs | Key Performance Indicators | Planned Targets |  |  | Achieved Targets |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 2023/24 | 2024/25 | 2025/26 | 2023/24 | 2024/25 | 2025/26 |  |
| Programme 1: 1014000 Irrigation and Land Reclamation |  |  |  |  |  |  |  |  |  |  |
| Outcome: Enhanced utilization of land through irrigation, drainage and land reclamation |  |  |  |  |  |  |  |  |  |  |
| 11014020 Land Reclamation | 1104000100 Land Reclamation Services | Land Reclamation Policy and legal framework | Land Reclamation Policy | 1 | 1 | 1 | 0 | 0 | 1 | Draft policy in place awaiting Cabinet approval |
|  |  |  | Land Reclamation Bill | - | 1 | 1 | - | 0 | 0 | Draft LR Bill was presented to Attorney General team for refinement and then presented to the Sector Working Group (SWAG) and Parliamentary Affairs. Public participation was not done due to insufficient funds and is planned for 2026/27 |
|  | Land Reclamation (Land Degradation Assessment Program) | Land Degradation Assessment Reports | No. of Assessment studies conducted and disseminated | 2 | 4 | - | 0 | 2 | - | Middle Tana and Middle Mara completed in 2024/25 Machakos and Siaya Sub-catchment reports not completed |
|  | 1104104600 Land Reclamation for Climate Resilience & Livelihood Enhancement | Water harvesting structures constructed | No of water harvesting structures | - | 4 | 4 | - | 0 | 4 | Target achieved. 3 water pans and a silt pan done in Griftu,Wajir County |
|  |  |  | Volume in cubic meters achieved | - | 600,000 | 420,000 | - | 180,000 | 780,000 | Overachievement due to review of the designs which increased the contracted volume by 150,000 M3 and a silt pan of 50,000 M3. |
|  | 1104100200 Small Holder Irrigation Programme | Land put under irrigation | No. of acres developed | 860 | 1,300 | - | 0 | 1,300 | - | Targeted area of 1300 acres achieved in 2024/25 |
|  |  | Farmers cooperatives trained | No. trained | - | - | 5 | - | - | 5 | The five (5) smallholder irrigation projects (i.e. Gatene, Miuka, Kandeki, Kiramanthi and Magatianthi) were capacity built on O&M |
|  | 1104100400 Bura Irrigation Scheme | Land rehabilitated and put under irrigation | Total No. of acres rehabilitated | 5,550 | 4,492 | 6,516 | 4,300 | 6,300 | 8,300 | This is a cumulative target. The target for 2025/26 was to increase the rehabilitated area by 216 acres to have the total area rehabilitated at 6,516 acres. As a result of water flow via gravity, rehabilitation of 2,000 acres was accelerated to settle farmers who had not been allocated land in the scheme. |
|  |  | Bura Gravity Canal | % completion | 100 | 100 | 97 | 91 | 93.77 | 100 | Target Achieved |
|  | 1104100600 Community Based Irrigation Projects. | Land put under Irrigation. | No. of acres | 920 | 1,300 | 3,000 | 750 | 1,300 | 2,762 | Underachievement due to flooding in Entasopia block (350acres) in Nguruman, Acres achieved by completing Kaihi -1,600 acres, Kibugu Nguviu- 662 acres, Laghale -100 acres and Nguruman (Oloibortoto block) 400 acres. |
|  | 1104100700 Galana Kulalu Irrigation development project | Land under crop production | No. of acres in the model farm cropped | 5,100 | 1,300 | 3,300 | 538 | 1,500 | 2,970 | The project had 2,000 acres under seed maize and 970 acres were under Chia seed production. The reported under achievement was as a result of low uptake by the private party. |
|  |  | Maize produced | No. of tons | - | 3,900 | 9,900 | - | 1,614 | 3,295 |  |
|  |  | Galana Model Farm (10,000 acres) | % completion | 100 | 100 | 100 | 99 | 99 | 100 | Target Achieved. |
|  | 1104100800 National expanded irrigation Programme | Land put under Irrigation. | No. of acres developed | 10,900 | 15,540 | 1,650 | 7,294 | 12,125 | 7,978 | Over achievement of 6,328 acres due to enhanced budgetary allocation during Supplementary budget which enabled completion of multi-year projects. Under achievement in the outer years was due to budget cuts. |
|  | Mwea Irrigation Development project (Thiba Dam and Irrigation Area) | Area under irrigation developed | No. of acres | 35,000 | 35,000 | 31,000 | 30,600 | 30,600 | 31,000 | Target Achieved. |
|  |  | Rice produced | No. of Tons of paddy produced | 93,270 | 150,000 | 160,300 | 131,760 | 160,297 | 179,086 | Over achievement was as a result of cropping the scheme for 3 seasons (main, ratoon and double crop) as a result of sufficient irrigation water from Thiba Dam. |
|  | 1104101300 Turkana Irrigation Development Project | Land put under Irrigation. | No. of acres under irrigation | 1,200 | 430 | 240 | 4,064 | 500 | 387 | In FY2023/24, priority was given to rehabilitation of Katilu and Lokubae Irrigation Schemes which had been destroyed by floods. |
|  | 1104101500 Lower Kuja Irrigation Scheme | Land put under Irrigation | No. of acres | 1,000 | 1,145 | 1,000 | 1,330 | 1,145 | 800 | Under achievement because priority was given to compensation of PAPs, in order to pave way for progression of works. |
|  |  | Rice produced | No. of Tons of paddy produced | 1270 | 3,091 | 2,700 | 1689 | 3,120 | 2,160 | The realized tonnage was from the acreage expanded in the period |
|  | 1104101700 Kenya Water Security & Climate Resilience (Prj Advanced). (KWSCRP-I) | Lower Nzoia Irrigation infrastructure completed | % completion | 100 | 90 | - | 72 | 91 | - | This project was transferred to the State Department for Water and Sanitation |
|  | 1104101800 Water Security & Climate Resilience Prj KWSCRP-II Mwache Dam Phase I | Mwache Dam Constructed | % completion of project | 20 | 35 | - | 12.60 | 44 | - | This project was transferred to the State Department for Water and Sanitation |
|  | 1104102000 Drought Resilience Program in Northern Kenya | Water harvesting structures constructed | No. of water harvesting structures | 29 | 50 | 25 | 0 | 11 | 19 | 5 water pans constructed with a volume of 118,000M3 ,7 boreholes drilled ,5 water reticulation and 2 underground water tanks |
|  | 1104102700 Water Security and Climate Adaptation in Mandera and Wajir Clusters | Water Storage Capacity achieved | Volume in Cubic meters of water pan excavated | 495,000 | - | - | 140,000 | - | - | Target was not achieved in 2023/24 due to a 65% budget cut. |
|  | 1104104000 Suba clusters Irrigation Development Project | Nyamaji Irrigation Project (1,000 acres) completed | % completion | - | - | 50 | - | - | 53.7 | Target Achieved |
|  |  | Sindo Irrigation Project (1,889 acres) completed | % completion | - | - | 10 | - | - | 10 | Target Achieved |
|  | 1104103900 Hola Irrigation Development Project - Phase2 | Hola Irrigation Development Project - Phase 2 feasibility study and detailed design review | Reviewed Feasibility Study and Detailed Design Report | 1 | - | - | 0 | - | - | The allocation for FY23/24 was Kshs 30M, the bid was non-responsive because the allocation was below the quoted market price . |
|  | 1104104100 Lining of Canal - Mwea Irrigation Scheme Projects | Conveyance and distribution canal lined | No. of Kilometers | 1 | - | - | 1.8 | - | - | The reported achievement was as a result of prioritization of lining the branch canals instead of the main canal in the scheme. |
|  | 1104104200 Upgrading of Ahero Irrigation Development Project | Ahero Irrigation Development Project upgraded | % completion | - | - | 40 | - | - | 57 | The positive variance realized as a result of accelerated works by the contractor to prevent disruptions during the rainy season. |
|  | 1104102500 Spate Irrigation for Climate Resilience Samburu, Marsabit & Isiolo | Water Storage Capacity achieved | Volume in Cubic meters of water pan excavated | 450,000 | - | - | 210,000 | - | - | Target was not achieved in 2023/24 due to a 50% budget cut. |
|  | 1104103500 Irrigation projects for food security – Rice production expansion | Land put under Irrigation | No. of acres | - | - | 2,000 | - | - | 2,000 | Target Achieved |
|  | 1104103600 National Irrigation Authority–Drought Mitigation projects | Area under irrigation developed | No. of acres | - | 4,000 | - | - | 5,400 | - | Over achievement due to fast-tracking of the works after payment of outstanding certificates |
|  | 1104104300 National Irrigation Authority Irrigation Projects | Land put under Irrigation | No. of acres | - | 80 | 800 | - | 0 | 2400 | Over achievement of 1,600 acres due to enhanced budgetary allocation during Supplementary budget which enabled completion of multi-year projects. |
|  | 1104104501Balich - Abdisamet Irrigation Project | Irrigation infrastructure completed | % completion | 20 | 60 | 80 | 10.2 | 47 | 80 | Target Achieved. Project is ongoing. |
|  | 1104103700 Irrigation Sector Reform Programme | Irrigation Licensing Unit operationalized | Irrigation scheme licensing unit in place | - | 1 | - | - | 1 | - | Target was achieved in 2024/25 |
|  |  | Technical support to Counties to form CIDUs | No of CIDUs Formed | - | 12 | 12 | - | 12 | 12 | Target was achieved |
|  |  | CIDUs capacity built on development of policy instruments | No. of CIDUs trained on development of policy instruments | - | 12 | 5 | - | 1 | 5 | Underachievement in fy 24/25 was due to 50% budget cuts |
|  |  | Irrigation schemes Licensed | No. of irrigation schemes licensed | - | 50 | 15 | - | 4 | 8 | Under achievement attributed to IWUAs’ lack of prerequisite regulatory requirements |
|  |  | Irrigation service providers Registered | No. of irrigation service providers registered | - | 20 | 10 | - | 0 | 11 |  |
|  |  | Compliance to irrigation quality standards through the QMS toolkit in irrigation schemes | No. of irrigation schemes assessed | - | - | 12 | - | - | 12 | Target achieved |
|  | 1104103400 Monitoring an d Evaluation of Projects | Projects Monitored and Evaluated | No. of Projects Monitored and Evaluated | 73 | 91 | 150 | 73 | 91 | 87 | Under achievement due to inadequate budgetary allocation |
|  | 1104104700 Programme for enhancement of water productivity, production and sustainability of Irrigation Schemes (PEWaPPSIS) | Schemes performance assessment | No. of schemes assessed | - | 10 | 12 | - | 13 | 6 | Target Underachieved due to insufficient funds |
|  |  | IWUAs registered and trained | Number of IWUAs registered and trained | - | 20 | 30 | - | 20 | 9 | Available budget could only facilitate capacity building of 9 schemes |
|  |  | Schemes installed with water meters | Number of Schemes installed with water meters | - | 3 | 6 | - | 3 | 2 | Meters were installed in Githuya and Gacharaigu schemes |
| Programme 2: 1017000 Water Storage and Flood Control Programme |  |  |  |  |  |  |  |  |  |  |
| Outcome: Increased per capita water storage capital and flood control. |  |  |  |  |  |  |  |  |  |  |
| S.P 3.1: Water Storage and Flood Control | 1104102100 Flood Control Works | Dykes constructed | No. of Kilometers constructed | 15 | 4.55 | - | 13 | 4.55 | - | Functions were transferred to the State Department for Water and Sanitation through Executive Order No. 1 of 2025 |
|  |  | Check dams constructed | No of check dams constructed | 5 | 2 | - | 1 | 3 | - |  |
|  |  | River training done | No. of Kilometers excavated | 1.5 | - | - | 0 | - | - |  |
|  |  | Flood control structures maintained | No. of Kilometers | 3 | 0.5 | - | 0 | 1 | - |  |
|  | 1104102200 Siyoi-Muruny Water Project | Siyoi-Muruny Dam and Water Supply constructed | % completion | 100 | 93.5 | - | 84 | 91 | - |  |
|  | 1104102300 Umaa Dam | Umaa Dam constructed | % Completion | 69 | 76.6 | - | 69 | 78.24 | - |  |
|  | 1104103100 Soin - Koru Dam | Water Dam Constructed | % completion | 6 | - | - | 6 | - | - |  |
| Programme 4: Water Harvesting and Storage for Irrigation |  |  |  |  |  |  |  |  |  |  |
| Outcome: Increased per capita water storage capacity for irrigation |  |  |  |  |  |  |  |  |  |  |
| SP 4.1 Water Storage for Irrigation | 11041212200 Rehabilitation of Strategic Water Facilities | Strategic water harvesting facilities De-silted | Volume in cubic meters | - | 1,400,000 | 220,000 | - | 1,412,000 | 260,000 | Target achieved as a result of enhanced budgetary allocation during supplementary by 110%. |
|  | 1104103000 Development of Large-Scale Multi-Purpose Dams | Feasibility studies for PPP Undertaken | No. of studies | 4 | 6 | - | 3 | 8 | - | Feasibility studies completed for New Gogo, Radat, Thuci, Lowaat, Lower Turkwel, Bosto, Galana Downstream, Barsalinga (Isiolo) dam,High Grand Falls,Yatta dam and Soin Koru. |
|  |  | PPP Projects pipelined | No. of projects pipelined | - | - | 8 | - | - | 1 |  |
| SP 4.2: Water Harvesting for Irrigation | Micro Irrigation Programme for School | Public schools equipped with boreholes, greenhouses and irrigation kits | No. of public schools equipped. | 10 | 15 | 6 | 10 | 6 | 11 | Over-achievement due to additional funding from supplementary budgetary allocation. |
|  | Household Irrigation Water Harvesting Project | Water Storage Capacity achieved | Volume in Cubic meters of water pans excavated | 5,600,000 | 5,625,000 | 108,000 | 4,668,000 | 2,174,077 | 108,000 | Target not achieved due to budget cuts in 2023/24 and 2024/25 |
| Programme:1023000 General Administration, Planning and Support Services |  |  |  |  |  |  |  |  |  |  |
| Outcome: Good governance and management of irrigation resources |  |  |  |  |  |  |  |  |  |  |
| 1023010 Administrative Services | 1104000400 Headquarters Administration - Irrigation | Government Services Digitalized and onboarded | % of Citizen-facing services digitalized and on-boarded | 100 | 100 | 100 | 100 | 100 | 100 | Target achieved |
|  |  |  | No. of back-office services digitalized and on-boarded | - | 3 | - | - | 4 | - | Target achieved |
|  |  | Medium-Term Expenditure Framework coordinated | MTEF Sub-sector Budget Proposal | 1 | 1 | 1 | 1 | 1 | 1 | Target achieved |

# 2.2 ANALYSIS OF EXPENDITURE TRENDS FOR THE FY 2023/24 – FY 2025/26

This section presents analysis of recurrent and development expenditures as well as SAGAs recurrent budget versus actual expenditure.

Table 2. 2: Analysis of Recurrent Expenditure (KSh. Million)

| Economic Classification | Approved Budget Allocation |  |  | Actual Expenditure |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2023/24 | 2024/25 | 2025/26 | 2023/24 | 2024/25 | 2025/26 |
| Gross | 1,554.00 | 1,387.00 | 1,130.67 | 1,542.00 | 1,379.36 | 1,118.58 |
| AIA | 408.00 | 358.00 | 308.00 | 289.00 | 358.00 | 307.98 |
| Net-Exchequer | 1,146.00 | 1,029.00 | 822.67 | 1,253.00 | 1,021.36 | 810.60 |
| Compensation of Employees | 210.46 | 232.00 | 282.08 | 210.00 | 231.00 | 282.08 |
| Transfers | 1,221.00 | 1,105.00 | 768.01 | 1,221.00 | 1,104.36 | 767.99 |
| Other Recurrent | 122.54 | 50.00 | 80.58 | 111.00 | 44.00 | 68.51 |
| Utilities | - | - |  | - | - |  |
| Rent | - | 4.00 | 4.10 | - | 4.00 | 3.97 |
| Insurance | - | - |  | - | - |  |
| Subsidies | - | - |  | - | - |  |
| Gratuity | - | - |  | - | - |  |
| Contracted Guards & Cleaners Services | 3.00 | 3.00 | 3.10 | 3.00 | 3.00 | 3.00 |
| Use of Goods and Services | 119.54 | 43.00 | 73.38 | 108.00 | 37.00 | 61.54 |

The State Department Allocation decreased by Kshs. 167 million in FY 2024/25 as compared to FY 2023/24 and further by Kshs 256 million a result of transfer of National water Harvesting and Storage Authority from the State Department to the State Department for Water and Sanitation through the Executive Order No.1 of 2025 as well as budget reduction of transfers to both NIA and NWHSA in the FY 2024/25. The absorption rates have been maintained at 99% over the period under review.

# Table 2. 3: Analysis of Development Approved Budget Vs Actual Expenditure (Ksh. Million)

| Vote and Vote Details | Description | Approved Budget Allocation |  |  | Actual Expenditure |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Vote 1104: State Department for Irrigation |  | 2023/24 | 2024/25 | 2025/26 | 2023/24 | 2024/25 | 2025/26 |
|  | Gross | 20,604.00 | 18,255.00 | 10,934.57 | 17,720.00 | 17,887.00 | 8,869.50 |
|  | GoK | 11,942.00 | 9,183.00 | 8,395.47 | 11,711.00 | 9,070.00 | 8,174.93 |
|  | Loans | 8,492.00 | 8,772.00 | 1,621.00 | 5,959.00 | 8,520.00 | 601.36 |
|  | Grants | 170.00 | 300.00 | 918.10 | 50.00 | 297.00 | 93.21 |
|  | Local AIA | - |  |  | - |  |  |

The Sub-sector’s development approved budget significantly reduced by 47% in FY2023/24 as compared to FY2025/26 due to inter-departmental transfer of some projects to the State Department for Water and Sanitation from the State Department for Irrigation and other GOK budget reduction over the period under review.

The absorption rates increased 87% to 98% and reduced to 81% in FY2023/24, FY2024/25 and FY2025/26 respectively. The improved absorption rate in FY 2024/25 was mainly due to timely implementation of planned activities under the projects funded by both GoK and Donor Funds. The decrease in absorption rate in the FY 2025/26 was as a result of low absorption of Donor funded project (Drought Resilience Project in Northern Kenya) as result of implementation conditionalities which slowed the absorption.

# Table 2. 4: Analysis of Programme Approved Budget Vs Actual Expenditure (Ksh. Million)

|  | Approved Budget |  |  | Actual Expenditure |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Programme Details | 2023/24 | 2024/25 | 2025/26 | 2023/24 | 2024/25 | 2025/26 |
| P1. Irrigation and Land Reclamation |  |  |  |  |  |  |
| SP 1.1 Land Reclamation | 46.00 | 122.00 | 138.70 | 43.00 | 120.84 | 136.91 |
| SP 1.2 Irrigation and Drainage | 17,825.00 | 15,360.00 | 9,806.87 | 15,095.00 | 15,104.33 | 7,937.93 |
| SP 1.3 Irrigation Water Management | 190.00 | 267.00 | 210.71 | 185.00 | 263.83 | 206.56 |
| Total Programme 1 | 18,061.00 | 15,749.00 | 10,156.28 | 15,323.00 | 15,489.00 | 8,281.40 |
| P2.Water Storage and Flood Control |  |  |  |  |  |  |
| SP 2.1 Water Storage and Flood Control | 2,377.00 | 1,708.00 | - | 2,343.00 | 1,616.00 | - |
| Total Programme 2 | 2,377.00 | 1,708.00 | - | 2,343.00 | 1,616.00 |  |
| P3. Water Harvesting Storage for Irrigation |  |  |  |  |  |  |
| SP 3.1 Water Storage for Irrigation | 630.00 | 370.00 | 1,236.76 | 528.00 | 355.00 | 1,039.46 |
| SP 3.2 Water Harvesting for Irrigation | 921.00 | 1,662.00 | 480.57 | 906.00 | 1,659.00 | 480.57 |
| Total Programme 3 | 1,551.00 | 2,032.00 | 1,717.33 | 1,434.00 | 2,014.00 | 1,520.04 |
| P4. General Administration, Planning and Support Services |  |  |  |  |  |  |
| SP 4.1 Administrative Services | 169.00 | 153.00 | 191.64 | 162.00 | 147.36 | 186.65 |
| Total Programme 4 | 169.00 | 153.00 | 191.64 | 162.00 | 147.36 | 186.65 |
| Total Vote 1104 | 22,158.00 | 19,642.00 | 12,065.25 | 19,262.00 | 19,266.36 | 9,988.09 |

# Table 2. 5: Analysis of Programme Approved Budget Vs Actual Expenditure (Ksh. Million)

|  | Approved Budget |  |  | Actual Expenditure |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Economic Classification | 2023/24 | 2024/25 | 2025/26 | 2023/24 | 2024/25 | 2025/26 |
| PROGRAMME 1: IRRIGATION AND LAND RECLAMATION |  |  |  |  |  |  |
| Current Expenditure | 857.00 | 804.00 | 918.18 | 853.00 | 803.00 | 913.73 |
| Compensation of Employees | 85.00 | 90.00 | 124.17 | 85.00 | 91.00 | 124.17 |
| Use of Goods and Services | 46.00 | 17.00 | 25.16 | 42.00 | 15.00 | 20.74 |
| Grants and Other Transfers | 724.00 | 697.00 | 768.01 | 724.00 | 697.00 | 767.99 |
| Other Recurrent | 2.00 | - | 0.84 | 2.00 |  | 0.83 |
| Capital Expenditure | 17,204.00 | 14,945.00 | 9,238.10 | 14,437.00 | 14,686.00 | 7,367.67 |
| Acquisition of non-financial assets | 880.00 |  |  | 880.00 |  |  |
| Capital Grants to Government Agencies | 16,324.00 | 14,945.00 | 9,238.10 | 13,557.00 | 14,686.00 | 7,367.67 |
| Other Development | - |  |  | - |  |  |
| Total Expenditure of P1 | 18,061.00 | 15,749.00 | 10,156.28 | 15,290.00 | 15,489.00 | 8,281.40 |
| PROGRAMME 2: WATER STORAGE AND FLOOD CONTROL |  |  |  |  |  |  |
| Current Expenditure | 497.00 | 408.00 | - | 496.00 | 408.00 | - |
| Compensation of Employees | - |  |  | - |  |  |
| Use of Goods and Services | - |  |  | - |  |  |
| Grants and Other Transfers | 497.00 | 408.00 |  | 496.00 | 408.00 |  |
| Other Recurrent | - |  |  | - |  |  |
| Capital Expenditure | 1,880.00 | 1,300.00 | - | 1,880.00 | 1,208.00 | - |
| Acquisition of non-financial assets | - |  |  | - |  |  |
| Capital Grants to Government Agencies | 1,880.00 | 1,300.00 |  | 1,880.00 | 1,208.00 |  |
| Other Development | - |  |  | - |  |  |
| Total Expenditure of P2 | 2,377.00 | 1,708.00 | - | 2,376.00 | 1,616.00 | - |
| PROGRAMME 3: WATER HARVESTING AND STORAGE FOR IRRIGATION |  |  |  |  |  |  |
| Current Expenditure | 31.00 | 22.00 | 20.86 | 31.00 | 21.00 | 18.20 |
| Compensation of Employees | 20.00 | 15.00 | - | 20.00 | 15.00 |  |
| Use of Goods and Services | 9.00 | 6.00 | 19.00 | 9.00 | 5.00 | 17.35 |
| Grants and Other Transfers | - |  |  | - |  |  |
| Other Recurrent | 2.00 | 1.00 | 1.86 | 2.00 | 1.00 | 0.86 |
| Capital Expenditure | 1,520.00 | 2,010.00 | 1,696.47 | 1,403.00 | 1,993.00 | 1,501.83 |
| Acquisition of non-financial assets | 290.00 | - |  | 256.00 |  |  |
| Capital Grants to Government Agencies | 1,230.00 | 2,010.00 | 1,696.47 | 1,147.00 | 1,993.00 | 1,501.83 |
| Other Development | - | - |  | - |  |  |
| Total Expenditure of P3 | 1,551.00 | 2,032.00 | 1,717.33 | 1,434.00 | 2,014.00 | 1,520.04 |
| PPROGRAMME 4: GENERAL ADMINISTRATION, PLANNNING AND SUPPORT SERVICES |  |  |  |  |  |  |
| Current Expenditure | 169.00 | 153.00 | 191.64 | 162.00 | 147.36 | 186.65 |
| Compensation of Employees | 106.00 | 126.00 | 157.91 | 106.00 | 125.00 | 157.91 |
| Use of Goods and Services | 47.00 | 26.00 | 31.47 | 40.00 | 22.00 | 27.54 |
| Grants and Other Transfers | - |  |  | - |  |  |
| Other Recurrent | 16.00 | 1.00 | 2.25 | 16.00 | 0.36 | 1.20 |
| Capital Expenditure | - | - |  | - | - |  |
| Acquisition of non-financial assets | - | - |  | - | - |  |
| Capital Grants to Government Agencies | - | - |  | - | - |  |
| Other Development | - | - |  | - | - |  |
| Total Expenditure of P4 | 169.00 | 153.00 | 191.64 | 162.00 | 147.36 | 186.65 |
| Vote 1104: State Department for Irrigation | 22,158.00 | 19,642.00 | 12,065.25 | 19,262.00 | 19,266.36 | 9,988.09 |

# Table 2. 6: Analysis of SAGAs Recurrent Budget Vs. Actual Expenditure (Ksh. Million)

| Economic Classification | Approved Budget |  |  | Actual Expenditure |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2023/24 | 2024/25 | 2025/26 | 2023/24 | 2024/25 | 2025/26 |  |
| NATIONAL IRRIGATION AUTHORITY |  |  |  |  |  |  |  |
| GROSS | 724 | 697 | 768 | 658 | 697 | 768 |  |
| AIA - Internally Generated Revenue | 308 | 308 | 308 | 243 | 308 | 308 |  |
| Net-Exchequer | 416 | 389 | 460 | 415 | 389 | 460 |  |
| Compensation of Employees | 416 | 409 | 460 | 389 | 409 | 460 |  |
| Use of Goods and Services | 308 | 288 | 308 | 269 | 288 | 308 |  |
| Of which |  |  |  |  |  |  |  |
| Insurance | 51 | 42.7 | 47.7 | 51 | 42.7 | 47.7 |  |
| Utilities | 8 | 6.5 | 8 | 8 | 6.5 | 8 |  |
| Rent | 1 | 0.6 | 1.1 | 1 | 0.6 | 1.1 |  |
| Subsidies | - | - | - | - | - | - |  |
| Gratuity | 11 | 11 | 11 | 11 | 11 | 11 |  |
| Contracted Professional (Guards & Cleaners) | 4 | 3.5 | 4 | 4 | 3.5 | 4 |  |
| Others specify | 233 | 223.7 | 236.2 | 194 | 223.7 | 236.2 |  |
| TOTAL | 724 | 697 | 768 | 658 | 697 | 768 |  |
| NATIONAL WATER HARVESTING AND STORAGE AUTHORITY |  |  |  |  |  |  |  |
| GROSS | 498 | 408 |  | 451 | 408 |  |  |
| AIA - Internally Generated Revenue | 100 | 50 |  | 53 | 50 |  |  |
| Net-Exchequer | 398 | 358 |  | 398 | 358 |  |  |
| Compensation of Employees | 403 | 338 |  | 358 | 338 |  |  |
| Use of Goods and Services | 95 | 70 |  | 93 | 70 |  |  |
| Of which |  |  |  |  |  |  |  |
| Insurance | 8 | 2 |  | 8 | 2 |  |  |
| Utilities | 11 | 6 |  | 11 | 6 |  |  |
| Rent | - |  |  | - | 0 |  |  |
| Subsidies | - | 0 |  | - | 0 |  |  |
| Gratuity | - | 0 |  | - | 0 |  |  |
| Contracted Professional (Guards & Cleaners) | 26 | 31 |  | 26 | 31 |  |  |
| Others Specify |  |  |  |  |  |  |  |
| Remuneration of Directors | 25 | 29 |  | 25 | 29 |  |  |
| Legal Expenses | 9 | 0 |  | 8 | 0 |  |  |
| Audit Fees | 2 | 2 |  | 2 | 2 |  |  |
| Monitoring & Evaluation | - | 0 |  | - | 0 |  |  |
| Staff Welfare | 6 | 0 |  | 5 | 0 |  |  |
| Stationery & Others | 8 | 0 |  | 8 | 0 |  |  |
| Transfers | - | 0 |  | - | 0 |  |  |
| TOTAL | 498 | 408 |  | 451 | 408 |  |  |

# 2.3 ANALYSIS OF PERFORMANCE OF CAPITAL PROJECTS FY 2023/4 – 2025/26

# Table 2. 7: Analysis of Performance of Capital Projects FY 2023/24 – 2025/26

| PROJECT CODE & PROJECT TITLE | Estimated cost of the Project |  |  | Timeline |  | FY 2023/2024 Approved Budget |  |  |  | FY 2024/2025 Approved Budget |  |  |  | FY 2025/2026 Approved Budget |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Total Estimated cost of Project | GoK | Foreign Financed | Start Date | Expected completion Date | Approved GOK Budget | Approved Foreign Financed Budget | Cumulative expenditure as at 30th June 2024 | Completion status as at 30th June 2024 (%) | Approved GOK Budget | Approved Foreign Financed Budget | Cumulative expenditure as at 30th June 2025 | Completion status as at 30th June 2025 (%) | Approved GOK Budget | Approved Foreign Financed Budget | Cumulative expenditure as at 30th June 2026 | Outstanding Balance as at 30th June 2026 | Completion status as at 30th June 2026 (%) | Remarks |
| PROGRAMME 2 : 1014000 IRRIGATION AND LAND RECLAMATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Subprogramme 2.1: 1014020 Land Reclamation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1104100500 Land Reclamation (Land Degradation Assessment Program). | 394 | 394 | 0 | 01-Jul-13 | 30-Jun-2030 | 10 | - | 106 | 27% | 20 | - | 126 | 32% | 0 | 0 | 126.00 | 268 | 32% | Land Degradation Assessment (LADA) program are studies that enable determination of extent and severity of land degradation using GIS and Remote sensing tools. A National LADA and five (5) sub catchment LADAs namely, Lake Magadi, Upper Ewaso Nyiro North, Upper Kerio river, Middle Tana and Middle Mara (Talek) sub basins have been done. Preliminary reports have been done for Machakos and Siaya sub catchments. |
| 1104104600 Land reclamation and restoration for climate resilience and livelihood enhancement programme | 8,500 | 8,500 | 0 | 01-Jul-24 | 01-Jun-34 | - | - | - | - | 60 | - | 60 | 1% | 90 | 0 | 149.90 | 8,350 | 2% | The project aims at improving water retention capacity on land for increased productivity through sustainable land use management, harvest and store water from intermittent streams (lagghas) for irrigated pasture production and to build climate resilience by buffering communities residing in ASAL areas against extreme weather events such as drought and floods. To date, Griftu water pans in Wajir County have been excavatedto a volume of 780,000m3. |
| Sub-Total SP 2.1 | 8,894 | 8,894 | - |  |  | 10 | - | 106 |  | 80 | - | 186 |  | 90 | - | 275.90 | 8,618 |  |  |
| Subprogramme 2.2: 1014030 Irrigation and Drainage |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1104100200 Small Holder Irrigation Programme | 1,383 | 195 | 1,188 | 01-Feb-16 | 01-Dec-26 | 20 | 100 | 568 | 41% | 7 | 482 | 1,010 | 73% | 17 | 250 | 1205.00 | 178 | 99% | This programme seeks to construct five (5No.) irrigation projects in Mt. Kenya region and put 1,300 acres under irrigation. To date, five (5No.) have been substantially completed and are under Defects Liability Period. |
| 1104100400 Bura Irrigation Scheme | 8,551 | 5,149 | 3,402 | 01-May-13 | 01-Jun-26 | 450 | 240 | 6,432 | 91% | 250 | 430 | 7,023 | 94% | 100 | 50 | 7198.80 | 1,352 | 100.00% | The project seeks to increase the acreage from the 12,000 to 25,000 acres. Both Lot 1 and Lot 2 are 98.5% complete supporting 12,000 acres. Review of the Lot 3 design is ongoing and the cost of rehabilitation estimated at Kshs. 4.9 billion. |
| 110400600 Community Based Irrigation Projects | 20,000 | 20,000 | 0 | 01-Jul-11 | 01-Jun-30 | 870 | - | 6,263 | 31% | 880 | - | 7,191 | 36% | 1752.1 | 0 | 8885.40 | 11,115 | 44% | The project aims at increasing the area under irrigation by at least 50,000 acres, benefitting over 100,000 households and 200,000 livestock units. In FY2025/26, 2,762 acres were put under irrigation. (Kaihi 1,600 acres, Kibugu Nguviu 662 acres, Laghale 100 acres and Nguruman (Oloibortoto block) 400 acres) |
| 1104100700 Galana Kulalu Irrigation development project (10,000). Galana Kulalu Food Security Project) | 9,677 | 2,382 | 7,295 | 01-Aug-14 | 01-Jun-30 | 444 | - | 8,215 | 99% | 500 | - | 8,715 | 99% | 123.6 | 0 | 8838.60 | 838 | 100% | The Project is aimed at putting 10,000 acres under irrigation to boost food security in the country. To date, 10,000 Acres Model Farm has been installed with the infrastructure and crop production is being done under PPP Model. |
| 1104100800 National Expanded Irrigation Programme | 123,930 | 123,930 | 0 | 01-Jun-12 | 01-Jun-30 | 2,500 | - | 36,358 | 29% | 1,503 | - | 37,960 | 31% | 1409.1 | 0 | 39369.10 | 84,561 | 32% | The programme aims to put 500,000 Acres under irrigation across the country. To date 166,956 Acres has been developed with 7,978 acres added in FY 2025/26. |
| 1104100900 Mwea Irrigation Development project (Thiba Dam and Irrigation Area) | 23,765 | 11,537 | 12,228 | 01-Feb-11 | 01-Dec-26 | 545 | 1,494 | 20,001 | 87% | 400 | 189 | 20,514 | 89% | 150 | 70 | 20706.50 | 3,059 | 99% | The project aims to increasing the acreage in Mwea Irrigation Scheme from 25,000 Acres to 35,000 Acres through construction of 15.5MCM Thiba Dam and in irrigation area. To date, package 1 is 100% complete while package 2, is at 85% complete. The project has currently put 31,000 acres under irrigation. |
| 1104101000 Rwabura Irrigation Development Project. | 1,265 | 208 | 1,057 | 01-Jul-16 | 01-Dec-25 | 10 | 743 | 1,024 | 100% | 8 | 100 | 1,034 | 100% | 0 | 100 | 1231.74 | 33 | 100% | The project aimed to put 1,500 Acres under Irrigation. The construction works have been completed. However, the project was affected by landslides during the DLP. |
| 1104101300 Turkana Irrigation Development Project. | 9,197 | 9,197 | 0 | 01-Jun-16 | 01-Jun-30 | 200 | - | 1,119 | 12% | 80 | - | 1,199 | 13% | 80 | 0 | 1279.00 | 7,918 | 14% | In the short and medium term, 172,100 Acres has been aimed for development using surface water through rehabilitation, expansion of existing schemes and development of new schemes. To date a total of 10,887 Acres has been developed. |
| 1104101500 Lower Kuja Irrigation Scheme | 4,694 | 4,694 | 0 | 01-May-16 | 01-Jun-30 | 150 | - | 793 | 34% | 100 | - | 893 | 19% | 80 | 0 | 973.00 | 3,721 | 21% | The project aims at putting 19,293 Acres under irrigation in Migori County. To date 9,683 Acres has been developed and put under irrigation. |
| 1104102000 Drought Resilience Program in Northern Kenya | 3,901 | 394 | 3,507 | 01-Jul-19 | 01-Dec-27 | 45 | 265 | 638 | 16% | 45 | 571 | 1,218 | 35% | 20 | 1769 | 1530.28 | 2,371 | 40% | A multisectoral project aimed at increasing the resilience of pastoral communities to drought by constructing water storage facilities for both human and livestock use and livestock improvement activities. In FY 2025/26, 5 water pans were constructed, 7 boreholes drilled, 5 water reticulation and 2 underground water tanks constructed. |
| 1104102500 Spate Irrigation for Climate Resilience Samburu, Marsabit and Isiolo | 6,930 | 6,930 | 0 | 01-Jul-20 | 01-Jun-30 | 50 | - | 426 | 6% | - | - | 426 | 6% | 0 | 0 | 426.00 | 6,504 | 6% | The goal of the project is to put additional 375 acres under irrigation and ultimately achieve the target 53.5 MCM of water stored by 2028. To date, 3 MCM volume of water has been harvested. |
| 1104102700 Water Security and Climate Adaptation in Mandera and Wajir Clusters | 4,200 | 4,200 | 0 | 01-Jul-20 | 01-Jun-30 | 50 | - | 388 | 9% | - | - | 388 | 9% | 0 | 0 | 388.00 | 3,812 | 9% | The goal of the project is to harvest 15.12 million cubic meters of water to put additional 23,500 Acres by the year 2028 in Mandera and Wajir counties through construction of water harvesting infrastructure. To date, cumulatively 1,550,000 Cubic Meters irrigating 2,409 Acres has been harvested. |
| 1104103800 El-Gade Irrigation Project | 350 | 350 | 0 | 01-Jul-23 | 01-Jun-26 | 50 | - | 50 | 12% | - | - | 50 | 12% | 0 | 0 | 50.00 | 300 | 12% | The project aims to construct 5 No. social dams with individual capacities of 200,000m3-300,000m3 to irrigate 500 Acres for increased food security in the area. To date, 100,000 m3 volume has been realized. |
| 1104103900 Hola Irrigation Development Project Phase 2 | 5,747 | 977 | 4,770 | 01-Jul-23 | 01-Jun-30 | 30 | - | 30 | 2% | - | - | 30 | 2% | 0 | 0 | 30.00 | 5,717 | 1% | The project aims to increase the total area under irrigation to 4,086 hectares and guiding capacity building to farmers on good agricultural practices, strengthened Irrigation Water Users Association (IWUAs) and strong market linkages for their produce. Pre-feasibility study has been conducted. |
| 1104104100 Lining of canals - Mwea Irrigation Scheme project | 1,900 | 1,900 | 0 | 01-Jul-23 | 01-Jun-30 | 27 | - | 27 | 1% | - | - | 27 | 1% | 0 | 0 | 27.00 | 1,873 | 1% | The project aims to line 28km of main canals, 56km of branch canals and 106km of main feeder canals. To date, 1.8km of canal has been lined. |
| 1104104200 Upgrading of Ahero Irrigation Development Project | 770 | 125 | 645 | 01-Jul-23 | 01-Jun-30 | 50 | - | 50 | 1% | 30 | 200 | 208 | 27% | 0 | 300 | 302.79 | 467 | 57% | The project aims to increase area under irrigation by 1,000 acres through installation of a solar powered pumping station to support both the existing Ahero scheme and the expansion area of 1000 acres. To date, design studies have been done and materials mobilized to site. |
| 1104101700 Kenya Water Security and Climate Resilience (Project Advanced) (KWSCRP-I) | 20,990 | 2,890 | 18,100 | 01-Jan-12 | 01-Jul-25 | 326 | 3,020 | 17,154 | 72% | 100 | 2,900 | 19,965 | 91% | - | - | 19965.00 | 1,025 | - | The project entails construction of Lower Nzoia Irrigation Project (LNIP) and Improvement of Flood Mitigation Structures (IFMS); Flood Early Warning System (FEWS); Agricultural support and Value chain Management; Nzoia Watershed Management; Improvement of Water Supply Services; Development and use of Water Investment Framework; Water Sector Transition and Reforms and Water Resources Management and Planning. The project was transferred to the State Department for Water and Sanitation. |
| 1104101800 Water Security and Climate Resilience Project (KWSCRP-II) - Mwache Dam Phase I | 29,530 | 4,060 | 25,470 | 01-Jun-16 | 01-Dec-26 | 300 | 2,800 | 10,047 | 13% | 1,100 | 4,200 | 15,664 | 44% | - | - | 15664.00 | 13,866 | - | Construction of Mwache dam; Mwache Catchment Management; Water Supply Investments; Sanitation Investments; Sustainable Livelihoods Improvement Program and Upper Check Dam and Demonstration Irrigation Scheme. The project was transferred to the State Department for Water and Sanitation. |
| 1104103600 National Irrigation Authority -Drought Mitigation projects | 20,000 | 20,000 | 0 | 01-Jun-21 | 01-Dec-30 | 2,100 | - | 2,300 | 31% | 600 | - | 2,900 | 15% | 156.98 | 0 | 3056.98 | 16,943 | 16% | This programme aims at mitigating the ravaging impacts of drought in ASAL Counties. Cumulatively 3,390 acres have been put under irrigation. |
| 1104104300 National Irrigation Authority Irrigation Projects | 20,000 | 20,000 | 0 | 01-Jul-24 | 01-Jun-30 | - | - | - | - | 420 | - | 300 | 2% | 1377.17 | 0 | 1672.88 | 18,327 | 7% | The programme aims to develop irrigation projects through development, expansion and rehabilitation of irrigation projects. To date 550 acres have put under irrigation. |
| 1104104400 Smallholder Irrigation Devpt & Mgt in Semi-Arid Lands-SIDEMAN-SAL | 75 | 75 | 0 | 01-Jun-23 | 01-Jul-24 | 75 |  | 75 | 100% | - |  | 75 | 100% | - | - | - | - | - | The project aimed to rehabilitate, five (5No.) irrigation projects to put 1,337 acres under irrigation. It was completed in 2023/24 financial year. |
| 1104104900 Elinino Emergency Mitigation Programme | 70 | 70 | 0 | 01-Jul-24 | 01-Jul-24 | 70 | - | 70 | 100% | - | - | 70 | 100% | - | - | - | - | - | The project aimed to facilitate assessment and mapping of lagghas. The project completed in FY2023/24 |
| 1104104800 Balich-Abdisamet Water Supply Project | 500 | 500 | 0 | 01-Jul-24 | 01-Jun-27 | 100 |  | 89 | 10% | 130 | - | 219 | 47% | 100 | 0 | 316.11 | 184 | 70% | The project entails drilling of three (3No.) boreholes, water storage and reticulation for irrigation. 3No. boreholes have been drilled and equipped and 63km pipeline laid. |
| 1104104000 Suba Clusters Irrigation Development Project | 5800 | 957 | 4843 | 01-Jul-25 | 30-Jun-30 | - | - | - | - | - | - | - | - | 350 | 0 | 349.10 | 5,451 | 30% | The cluster has 9No. projects namely, Nyamaji 1 & 2, Nyandiwa, Olambwe, Rangwena, Nyagidha, Gwassi, Konyango and Sindo which target to put 18,400 acres under irrigation. To date, achievements include Nyamaji 1 which is 53.7% complete and Sindo Irrigation Project which has currently attained 10% physical completion. |
| 1104118500 Community Based Irrigation Boreholes | 285 | 285 | 0 |  |  | - | - | - | - | - | - | - | - | 65 | 0 | 58.00 | 227 | 20% | The projects aim to restore and increase access to irrigation water by 240,000 CM through construction and rehabilitation of irrigation projects in arid and semi-arid regions. |
| 1104118300 Githiru Irrigation Water Project | 35 | 35 | 0 | 01-Jul-25 | 30-Jun-26 | - | - | - | - | - | - | - | - | 35 | 0 | 32.65 | 2 | 5% | The allocation for FY 2025/26 funded feasibility studies, survey and detailed design for the project. |
| 1104121100 Tharaka Nithi/Meru Irrigation Project | 1400 | 1400 | 0 | 01-Jun-26 | 30-Jun-28 | - | - | - | - | - | - | - | - | 200 | 0 | 200.00 | 1,200 | 55% | This project aims to put 4,200 acres under irrigation for horticultural value chain in the project areas. The project will benefit approximately 2,000 households. Cumulatively, average project completion stands at approximately 55% across the cluster. |
| 1104121900 Wamoro Irrigation Project | 85 | 85 | 0 | 01-Jun-26 | 30-Jun-28 | - | - | - | - | - | - | - | - | 65 | 0 | 65.00 | 20 | 5% | The project aims to increase access to water by 340,000 CM through rehabilitation of water pans for the community that depends on it. The project is currently in the final stages of procurement. |
| 1104121000 Tunyo Chemoror Irrigation | 35 | 35 | 0 | 01-Jun-26 | 30-Jun-28 | - | - | - | - | - | - | - | - | 10 | 0 | 10.00 | 25 | 5% | The project aims to increase access to water by 300,000 CM and put 200 acres under irrigation to benefit 100 households. The project is currently in the final stages of procurement. |
| Total - Irrigation and Drainage 2.2 | 325,065 | 242,560 | 82,505 |  |  | 8,462 | 8,662 | 112,117 |  | 6,153 | 9,072 | 127,079 |  | 6,091 | 2,539 | 133,831 | 191,089 |  | - |
| Subprogramme 2.3: 1014040 Irrigation Water Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1104103700 Irrigation Sector Reform Programme | 900 | 900 | 0 | 01-Jul-23 | 01-Jun-30 | 10 | - | 7 | 1% | 60 | - | 67 | 7% | 30 | 0 | 94.00 | 806 | 12% | The programme focuses on the following 1. Creating awareness on proposed irrigation sector reforms 2. Establishing new and restructuring existing institution 3. Building capacity of new and existing institutions to perform new roles 4. Developing Irrigation and Drainage management information system 5. Monitoring and regularly reporting on reforms 6. Coordinate implementation of reforms7.Licensing of all irrigation schemes |
| 1104104700 Programme for Enhancement of Water Productivity, Production and Sustainability of Irrigation Schemes (PEWaPPSIS) | 8,000 | 8,000 | 0 | 01-Jul-24 | 01-Jun-30 | - | - | - | - | 50 | - | 50 | 1% | 40 | 0 | 90.00 | 7,910 | 2% | The overall project objective is to improve food and nutrition security and increase household incomes amongst all beneficiaries in the approximately 2000 community-based schemes in the country by; improving irrigation scheme governance and water management, increasing irrigated production, promoting commercial irrigation to ensure profitability and sustainability of irrigation schemes. The programme has carried out mapping of irrigation schemes in 6 counties; developed improvement action plans for 6 irrigation schemes; increased water efficiency in 3 irrigation schemes through installation of 2 smart master meters, 300 smart individual meters and supply and installation of assorted pipes to 3 schemes; capacity building of 29 IWUAs and formulation of 8 IWUA trainers manuals |
| 1104103400 Monitoring and Evaluation of Projects | 1,000 | 1,000 | 0 | 01-Jul-23 | 01-Jun-30 | 60 | - | 56 | 6% | 130 | - | 186 | 19% | 80 | 0 | 263.44 | 737 | 26% | The programme aims at undertaking Monitoring and Evaluation of irrigation projects. A total of 178 irrigation projects have been monitored and evaluated. |
| Sub-Total for Irrigation Water Management 2.3 | 9,900 | 9,900 | - |  | - | 70 | - | 63 |  | 240 | - | 303 |  | 150 | - | 447.44 | 9,453 |  |  |
| PROGRAMME 3 : 1022000 WATER HARVESTING AND STORAGE FOR IRRIGATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Subprogramme 3.1: 1022020 Water Storage for Irrigation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1104102800 Rehabilitation of Strategic Water Facilities -NIA | 9,768 | 9,768 | 0 | 01-Jul-21 | 01-Jun-30 | 400 | - | 1,795 | 18% | 250 | - | 2,045 | 21% | 280 | 0 | 2324.90 | 7,443 | 24% | In FY 2025/26, Eight (8No.) water pans were developed and rehabilitated to harvest 0.3MCM of irrigation water. |
| 1104103500 Irrigation projects for food security - Rice production expansion | 6,800 | 6,800 | 0 | 01-Jul-22 | 01-Jun-30 | 30 | - |  | 1% | - | - | 90 | 1% | 500 | 0 | 563.57 | 6,236 | 5% | The project aims to increase access to water by 180,000 CM through construction of the dam for the community that depends on it. The project is currently in the final stages of procurement. |
| 1104103000 Development of Large-Scale Multi-Purpose Dams | 300,000 | 30,000 | 270,000 | 01-Jul-22 | 01-Jun-30 | 200 | - | 248 | 10% | 120 | - | 368 | 12% | 190 | 0 | 553.75 | 299,446 | 16% | The programme aims at increasing the volume of water harvested and stored for irrigation through construction of 19 large-scale multi-purpose dams. To date, eleven (11No.) pre-feasibility/feasibility studies have been completed. |
| 1104118200 Various Water Pans & Dams (Ardahalo Water Pan) | 50 | 50 | 0 | 01-Jul-25 | 30-Jun-26 | - | - | - | - | - | - | - | - | 50 |  | 46.55 | 3 | 93% | The project entails two (2No.) water pans were done with the total volume of 62,000 CM. |
| 1104121200 Rehabilitation of strategic water facilitites | 168 | 168 | 0 | 01-Jul-21 | 30-Jun-30 | - | - | - | - | - | - | - | - | 100.951 |  | 100.95 | 67 | 50% | The programme aims to restore and increase access to water by 672,000 CM through rehabilitation of existing water pans for communities that depend on them. Cumulative volume achieved to date is 260,000 CM with two (2No.) rehabilitated. |
| 110412300 Mobel Dam | 100 | 100 | 0 | 01-Jun-26 | 30-Jun-28 | - | - | - | - | - | - | - | - | 30 |  | 30.00 | 70 | 5% | The project aims to increase access to water by 180,000 CM through construction of the dam for the community that depends on it. The project is currently in the final stages of procurement. |
| 1104121400 Tendwo Dam | 67 | 67 | 0 | 01-Jun-26 | 30-Jun-28 | - | - | - | - | - | - | - | - | 50 |  | 50.00 | 17 | 5% | The project aims to increase access to water by 268,000 CM through construction of the dam for the community that depends on it. The project is currently in the final stages of procurement. |
| 1104121400 Wanifor Dam | 95 | 95 | 0 | 01-Jun-26 | 30-Jun-28 | - | - | - | - | - | - | - | - | 70 |  | 70.00 | 25 | 5% | The project aims to increase access to water by 380,000 CM through construction of the dam for the community that depends on it. The project is currently in the final stages of procurement. |
| 1104121701 Chiracha Waterpan Irrigation Project | 65 | 65 | 0 |  |  | - | - | - | - | - | - | - | - | 30 | 0 | 29.90 | 35 | 10% | The project aims to increase water storage by 75,600cubic benefitting over 5000households and livestock units. |
| 1104121600 Kapsinende Dam | 84 | 84 | 0 | 01-Jun-26 | 30-Jun-28 | - | - | - | - | - | - | - | - | 30 |  | 30.00 | 54 | 5% | The project aims to increase access to water by 336,000 CM through construction of the dam for the community that depends on it. The project is currently in the final stages of procurement. |
| Sub-Total SP 3.1 | 317,197 | 47,197 | 270,000 |  |  | 630 | - | 2,043 |  | 370 | - | 2,503 |  | 1,331 | - | 3,800 | 313,397 |  | - |
| Sub-programme 3.2: 1022020 Water Harvesting for Irrigation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1104101900 Micro Irrigation Programme for Schools. | 8,000 | 8,000 | 0 | 01-Jul-16 | 01-Jun-30 | 90 | - | 644 | 8% | 100 | - | 743 | 9% | 410 | 0 | 1153.00 | 6,847 | 14.41% | The programme is meant to equip 2,486 No. public primary and secondary schools lacking reliable water source, mainly those located in ASAL areas with borehole, elevated water tank and greenhouses with irrigation drip kits. A total of 122No. public schools has each benefited with drilled and equipped borehole, elevated tank (20M3) and greenhouses to date, with 10No. other projects ongoing. |
| 1104102600 Household Irrigation Water Harvesting Project | 30,000 | 30,000 | 0 | 01-Jul-19 | 01-Jun-30 | 800 | - | 6,535 | 22% | 940 | - | 7,475 | 25% | 223.6 | 0 | 7698.60 | 22,301 | 26% | The programme aims at increasing access to water at household level for agricultural production by 125 MCM in communities without traditional water sources through excavation of water pans. To date, 36,795 Household Water Pans have been constructed creating water storage capacity of 53.268MCM which has potential of putting 45,116 Acres under Irrigation. |
| Sub-Total SP 3.2 | 38,000 | 38,000 | - |  |  | 890 | - | 7,179 |  | 1,040 | - | 8,218 |  | 634 | - | 8851.60 | 29,148 |  |  |
| PROGRAMME 4: 1015000 WATER STORAGE AND FLOOD CONTROL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Subprogramme 4.1: 1015010 Water Storage and Flood Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1104103100 Soin-Koru Dam | 25,000 | 25,000 | 0 | 01-Aug-22 | 01-Aug-27 | 100 | - | 1,670 | 6% | - | - | 1,670 | 6% | - | - | - | - | - | The project entails construction of a 54m high earth dam, a 71,279m3/day water treatment plant, 1229KM of 800-300mm transmission line of treated water. The project was transferred to the State Department for Water and Sanitation. |
| 1104102200 Siyoi Muruny Water Project | 12,986 | 12,986 | 0 | 01-Mar-15 | 01-Mar-26 | 830 | - | 11,120 | 84% | 450 | - | 11,570 | 91% | - | - | - | - | - | The project entails construction of a 30m high earth dam, a 38,880m3/day water treatment plant, 17,865m3 storage tanks and 137kms of reticulation system to supply 38,880m3 / day of treated water to the residents of Kapenguria Municipality and its environs. The project was transferred to the State Department for Water and Sanitation. |
| 1104102100 Flood Control Works ESP | 3,500 | 3,500 | 0 | 01-Jul-05 | 01-Dec-27 | 530 | - | 1,992 | 75% | 400 | - | 2,392 | 78% | - | - | - | - | - | On completion, the programme will minimize the effects of floods in River Nyando in Kisumu County, River Kawalase in Turkanacounty, River Nzoia in Busia County, River Awase tende in Homa Bay County, River Sabwani in Tranzoia County, River Kuja in Migori County, River Perkerra in Marigat, Elgeyo Marakwet in Baringo County, Narok flood control, and Isiolo flood control by construction of 126.8 Km of dykes and 15 check dams. The project was transferred to the State Department for Water and Sanitation. |
| 1104102300 Umaa Dam | 3,726 | 3,726 | 0 | 01-Jun-09 | 01-Dec-26 | 250 | - | 1,434 | 69% | 130 | - | 1,564 | 78% | - | - | - | - | - | The project entails construction of a 28m high earth dam, a 2,500m3/day water treatment plant, and 1750 m of reticulation system to supply 2,500m3 / day of treated water to the residents of Kitui town and its environs. The project was transferred to the State Department for Water and Sanitation. |
| 1104101100 National Water Harvesting and Ground Water Exploitation | 600 | 600 |  | 01-Jun-24 | 01-Jun-30 | 120 | - | 120 | - | 220 | - | 248 | 57% | - | - | - | - | - | On completion, the programme will have added approximately 400,000 cubic metres of water to the national storage capacity through construction of 40 dams. The project was transferred to the State Department for Water and Sanitation. |
| Sub-Total SP 4.1 | 45,812 | 45,812 | - |  |  | 1,830 | - | 16,336 |  | 1,200 | - | 17,444 |  | - | - | - | - | - |  |
| Total for Vote 1104 State Department for Irrigation | 744,868 | 392,363 | 352,505 | - | #VALUE! | 11,892 | 8,662 | 137,844 |  | 9,083 | 9,072 | 155,733 |  | 8,296 | 2,539 | 147,205 | 551,706 |  |  |

# 2.4 REVIEW OF PENDING BILLS

This table presents a summary of pending bills incurred by the sub-sector during the period under review.

# Table 2. 8: Summary of Pending Bills

Pending bills categorized as due to lack of exchequer amounted to Ksh 186.51 under the period under review whereas the pending bills categorized as due to lack of provision amounting to Ksh. 781.2 are historical pending bills that relate to legal expenses that had crystallized as the court matters that were being handled and conclusively determined by the courts.

| Type/nature | Due to lack of exchequer |  |  | Due to lack of provision |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2023/24 | 2024/25 | 2025/26 | 2023/24 | 2024/25 | 2025/26 |
| 1.Recurrent |  |  |  |  |  |  |
| Compensation of employees | - | - | - | - | - | - |
| Use of goods and services e.g utilities, domestic or foreign travel etc | - | - | 14.21 | - | - | - |
| Social benefits e.g SHA, NSSF | - | - | - | - | - | - |
| Other expense | - | - | - | - | - | - |
| 2. Development |  |  |  |  |  |  |
| Acquisition of Non-Financial Assets | 190.88 | 256.81 | 172.30 | 781.2 | - | - |
| Use of goods and services | - | 496.35 | - | - | - | - |
| Others-Specify | - | - | - | - | - | - |
| Total Pending Bills | 190.88 | 753.16 | 186.51 | 781.2 | - | - |

# 2.5 SUMMARY OF COURT AWARDS

Table 2.9. presents a summary of sub-sector’s court awards for the period under review.

# Table 2. 9: Summary of Court Awards

| Details of the Award | Date of Award | Amount (Ksh Million) | Payment to date |
| --- | --- | --- | --- |
| Runji & Partners Consulting Engineers Vs. NWCPC in the matter of Arbitration (Badasa Dam) | 20/02/2018 | 18,760,068.00 | Nil |
| Runji & Partners Consulting Engineers Vs. NWCPC in the matter of Arbitration (Muruny (Muruny) Dam) | 10/08/2020 | 94,795,983.00 | Nil |
| Milimani HCCC No. 774 of 2010- Cowford General Contractors vs NWCPC | 29/01/2020 | 86,833,176.00 | Nil |
| J&K Investments K. Ltd Vs. NWHSA in the matter of Arbitration (Nakue’tum Peace Dam) | 31/11/2022 | 397,440,203.93 | Nil |
| Nakuru HCCC No 820 of 2011Anniversary Press (K)Ltd vs NWHSA | 25/11/2017 | 24,489,624.00 | Nil |
| NBI HCCC 107 of 2012 Assembled Enterprises versus NWCPC | 29/10/2021 | 4,630,537.92 | Nil |
| Drilling Spares Ltd Vs NWHSA | 5/12/2019 | 5,142,467.27 | Nil |
| Nairobi CMCC No. 2387 of 2020; Aurecon Amei Limited vs Otieno Odongo and Partners Consulting Engineering Limited & NWHSA | 4/06/2020 | 34,486,800.00 | Nil |
| MCCOMMSU/E1198 OF 2020 - Isaac Gathungu Wanjohi & Peter Scott Vs Draft & Develop Engineers Limited & NWHSA (Umaa Dam) | 1/07/2021 | 8,403,526.62 | Nil |
| Kaigi General Contractors Ltd Vs NIA | 20/06/2025 | 74,983,820 | Nil |
| Agrigreen Consulting Corps Ltd Vs NIA | 22/09/2023 | 51,551,915.75 | 7,000,000 |
| Strabag International GMBH Vs NIA | 19.04.2023 | 790,494,728.79 | Nil |
| Sogea Satom SAS Vs NIA | 26 .09.2023 | 740,924, 608 | Nil |
| Samima Investments Limited Vs State Law Office and The Principal Secretary Ministry of Water, Sanitation & Irrigation | 30.07.2025 | 131,962,800 | Nil |
| Total |  | 1,723,975,651.28 | 7,000,000 |

The total court awards to the State Department amounted to Kshs. 1,723,975,651.28. The non- settlement of the court awards has been due to lack of budgetary provision.